## Sheet1
Item # | Function | Start-date | End-Date | Status
1 | Add angular (In-Progress) | 2019-08-13 | 2019-08-19 | In-progress
2 | Add APIs | 2019-08-20 | 2019-08-23 | Not started
3 | Update Angular to use APIs | 2019-08-26 | 2019-09-06 | Not started
4 | Deploy docker local | 2019-09-09 | 2019-09-13 | Not started
5 | Config CI/CD | 2019-09-16 | 2019-09-20 | Not started
6 | Register Azure Account |  |  | Not started
7 | Add Docker Registry in Azure and config Auto CI/CD |  |  | Not started
8 | Add Wiki page |  |  | Not started
9 | Send to line manager |  |  | Not started